## testAnalysis_report
Section | Details
Project Name | ebay
Module Name | Login, Search, Add to Cart, Checkout, Order Management
Release Version | v1.0.0
s | Agile(sprint1)
Prepared By | Sulkshana Patil
Date | 2025-08-17
1. Test Summary
Metric | Count
Total Test Cases | 31
Executed Test Cases | 31
Passed Test Cases | 28
Failed Test Cases | 3
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | 25
Manual Test Cases | 6
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 28 | 90%
Failed | 3 | 10%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 3
Critical Defects | 0
High Severity Defects | 2
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 31 out of 31 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Price filter is unreliable it shows high range product also
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Password auto-suggestion missing | Medium | Open | Implement suggestion feature
Price filter includes out-of-range items | High | Open | Needs defect fix in backend filter query
7. Recommendations
Improve login input validation (strict username checks)